## Dashboard Summary (hidden)
Master Case ID | Master Case Title | Case Count | Service Category | Case Count
MC-01 | Transport – Buses (Timetable & Reliability) | 3 | Highways & Infrastructure | 10
MC-02 | Silverwoods / Netherton Lane (Planning & Road Impact) | 3 | Planning & Development | 10
MC-03 | Castle Inn (Planning, Visibility & Site Conditions) | 3 | Governance & Financial Scrutiny | 6
MC-04 | Malt Shovel Development Monitoring | 2 | Direct Resident Support | 5
MC-05 | Hitchens Way Adoption | 2 | Parking & Traffic Management | 3
MC-06 | Hawthorn Drive Footpath Safety | 3 | Transport (Buses) | 3
MC-07 | Highley Cycle Track Ownership & Maintenance | 2 | Environmental Health | 2
MC-08 | Covert Lane to Haggs Corner Deterioration | 1 |  | 39
MC-09 | Highley to Bewdley Deterioration | 1
MC-10 | Traffic Management (Strategic / Village-wide) | 1
MC-11 | Parking & Enforcement (Operational & Escalation) | 2
MC-12 | Governance & Financial Scrutiny | 11
MC-13 | Drainage & Surface Water (Infrastructure) | 3
MC-14 | Environmental Health (Sewage / Public Health) | 2
MC-15 | Direct Resident Support (Individual Cases) | 0
MC-16 | Building Control | 1
40
Outcome Definitions
Closed – No further action required from councillor perspective
Ongoing – Under monitoring or awaiting third-party response
Escalated – Formally raised beyond routine officer handling
Monitoring – Awaiting outcome following earlier intervention

## Casework Ledger
SL Ref | Master Case ID | Master Case Title | Category | Location | Issue / Activity | First Opened | Latest Update | Status | RAG | Comments
SL-01 | MC-01 | Transport – Buses (Timetable & Reliability) | Transport (Buses) | Highley | 08:21 service timing complaint; request for 08:21 to revert to 08:08 | Sept 2025 | 2026-04-01 | Open | Red | 125 service follow-up; continued chasing of council transport team; no reply. DB have agreed SC awaiting proforma from DB
SL-01 | MC-01 | Transport – Buses (Timetable & Reliability) | Transport (Buses) | Highley → Bridgnorth | Request for first bus timetable change | 2025-07-01 | Jan 2026 | Closed | Green
SL-04 | MC-02 | Silverwoods | Planning Enforcement | Highley | PEO attended 23.04. Site examined and all construction to date ties in with previous owners application. Request to move from three day rooms to two larger day rooms. Owners informed new planning application is required as previous was for different named individuals. SRS & PEO discussed jurisdiction near retirement park. Due to SC lack of provision for travellers, most planning objections are overturned as no alternative sites available. Deemed likely to go ahead and be approved. | Jan 2026 | 2026-04-01 | Open – Monitoring
SL-04 | MC-02 | Silverwoods / Netherton Lane (Planning & Road Damage) | Planning Enforcement | Netherton Lane | Construction traffic damage; remedial works agreed; exploring HGV restriction options - currently 2T | Jan 2026 | Jan 2026 | Open – Monitoring
SL-04 | MC-02 | Silverwoods / Netherton Lane (Planning & Road Damage) | Planning Enforcement | Silverwoods / Netherton Lane | Repairs outstanding; owner seeking advice; site meeting to be arranged with senior officer | Jan 2026 | Feb 2026 | Open – Monitoring
SL-04 | MC-02 | Silverwoods / Netherton Lane (Planning & Road Damage) | Planning Enforcement | Silverwoods - type & number of statics | Planning have advised one static is wider than the plan but not of significance to warrant enforcement | Jan 2026 | Jan 2026 | Closed | Green
SL-07 | MC-03 | Castle Inn (Planning, Visibility & Site Condition) | Planning & Highways | Castle Inn | Contentious fence approved by Planning Enforcement | Jan 2026 | Jan 2026 | Closed | Green
SL-08 | MC-03 | Castle Inn (Planning, Visibility & Site Condition) | Highways – Visibility | Woodhill Road / Castle Inn Slip Road | Hedge trimming completed; ownership clarified | Jun 2025 | Jan 2026 | Closed | Green
SL-09 | MC-03 | Castle Inn (Planning, Visibility & Site Condition) | Planning Enforcement | Castle Inn | Conifer order complied with; follow-up if highways element not forthcoming | Jan 2026 | Feb 2026 | Closed | Green
SL-10 | MC-04 | Malt Shovel Development Monitoring | Planning Enforcement | Malt Shovel | Bridlepath and development impact concerns escalated. PEO visited site 23.04. 24.04 lengthly conversation SRS with planning enforcement, viewed video and photo evidence of site being tidied. Seeding undertaken. Hedgerow to either be infilled or replanted. Owner requested to respond to PE. Approved for 25 accommodation units; compliance monitoring ongoing | Jan 2026 | 2026-04-01 | Open – Monitoring
SL-12 | MC-05 | Hitchens Way Adoption | Highways – Adoption | Highley, Hitchens Way | Adoption status clarification initiated; mapped as private; escalated Not adopted; sewer adoption prerequisite; re-engagement with developer | Jan 2026 | Feb 2026 | Open | Amber | 29.04 Phil ST speaking with dept responsible. ST sewerage report required - ST contacted and request submitted
SL-14 | MC-06 | Hawthorn Drive Footpath Safety | Highways – Pavements | Hawthorn Drive to Main Road | Adoption mapping corrected; works scheduled post-maintenance restart | Jan 2026 | Jan 2026 | Closed | Green | Highways to temporary fix and then resurface properly
SL-15 | MC-06 | Hawthorn Drive Footpath Safety | Highways – Pavements | Hawthorn Drive | Third safety incident escalated; priority request for full resurfacing new maintenance year/April. | Jan 2026 | Feb 2026 | Closed | Green
SL-16 | MC-06 | Hawthorn Drive Footpath Safety | Highways – Pavements | Hawthorn Drive to Main Road | Mobility scooter accident & visually impaired fall; formal escalation | Oct 2025 | Feb 2026 | Closed | Green
SL-17 | MC-07 | Highley Cycle Track Ownership & Maintenance | Infrastructure | Highley Cycle Track | Cycle track ownership/maintenance clarification initiated, Lapsed Sustrans agreement; no responsible body confirmed; legal/planning query underway | Jan 2026 | Feb 2026 | Open | Amber | 29.04 - chased up again to find contact details. GIS co-ordinates provided, awaiting SC notification of departmental owner
SL-19 | MC-08 | Covert Lane to Haggs Corner Deterioration | Highways – Roads | Covert Lane to top of Clee View | Severe carriageway deterioration; tyre damage reports; escalated via weekly Highways call | Feb 2026 | Feb 2026 | Closed | Green
SL-20 | MC-08 | Highley to Bewdley Deterioration | Highways – Roads | Highley out towards Bewdley | Severe carriageway deterioration; escalated; linked to rainfall | Feb 2026 | Feb 2026 | Closed | Green
SL-39 | MC-08 | Clee View Manhole Potholes | Highways – Roads | Covert Lane to Haggs Corner | Pot holes repaired | Feb 2026 | Feb 2026 | Closed | Green
SL-41 | MC-08 | Bynd Lane to Netherton Lane | Highways – Roads | Billingsley/Highley | Road either side of Ford in need of resurfacing: SRS to set up working party with Highways | Sept 2025 | Sept 2025 | Open |  | Highways evaluating and advising on plan to address. SRS investigating CIL contribution.
SL-21 | MC-10 | Traffic Management (Strategic / Village-wide) | Highways – Strategic | Highley | Village-wide traffic & road safety review initiated. CIL funded feasibility report shared with HPC Clerk | May 2025 | Oct 2025 | Open
SL-42 | MC-10 | Visibility on Vicarage Lane | Traffic Management | Highley | Arranged for convex mirror installed on Vicarage Lane | Feb 2026 | 2026-03-01 | Closed | Green
SL-45 | MC-10 | Coronation Street Road Sign | Traffic Management | Highley | Request for replacement road signage | 2026-04-01 |  | Open – Monitoring to ensure installation |  | Chased Highways and it has been ordered this week with an install date of mid/end June
SL-22 | MC-11 | Parking & Enforcement (Operational & Escalation) | Highways – Parking & Enforcement | Multiple Highley Streets | Parking enforcement report reviewed; liaison to ensure ongoing provision | Feb 2026 | 2026-04-01 | Closed | Green
SL-23 | MC-11 | Parking & Enforcement (Operational & Escalation) | Highways – Parking & Enforcement | Highley (various streets) | Resident congestion/parking complaints; enforcement engagement | Jan 2026 | 2026-04-01 | Closed | Green
SL-49 | MC-11 | 20MPH Ashley Gardens enforcement | Highways – Parking & Enforcement | Highley | Several residents have reported drivers ignoring the reduced speed limits around Highley Primary School and Ashleigh Gardens, particularly delivery and commercial vehicles. | 2026-04-01 |  | Open |  | Speeding noted. Spoke with Nick Newton and Simon D'Vali and it is accepted that it will not deter all drivers. Requested analysis of speed camera or speed bump provision. Neither available within current budget. Investigating CIL funding.
SL-30 | MC-13 | Drainage & Surface Water (Infrastructure) | Highways – Drainage | Highley | Blocked drains - drain clearing completed by SC | Sept 2025 | Sept 2025 | Closed | Green
SL-31 | MC-13 | Drainage & Surface Water (Infrastructure) | Highways – Drainage | Vicarage Lane | Flooding due to resurfacing ridge | Nov 2025 | Nov 2025 | Closed | Green
SL-32 | MC-13 | Drainage & Surface Water (Infrastructure) | Infrastructure – Drainage | Opposite Severn Centre | Surface water pooling following resurfacing; senior officers reviewing works | Jan 2026 | Feb 2026 | Closed | Green
SL-33 | MC-14 | Environmental Health (Sewage / Public Health) | Environmental Health / Utilities | Kinlet View & Netherfield | Persistent sewage odour investigation | May 2025 | 2025-04-01 | Open – Monitoring | Red | 29.04 Phil ST speaking with dept responsible. Meeting ST 27.03.26 on site
SL-39 | MC-14 | Environmental Health (Sewage / Public Health) | Flytipping | Pit Bank | Mattress in hedgerow - council kept rejecting stating it was on private land. Proved otherwise. Mattress removed | Jun 2025 | Feb 2026 | Closed | Green
SL-46 | MC-14 | Community Skip Provision and Recent Fly‑Tipping Concerns | Flytipping | Highley | Request for regular skip to aleviate fly tipping | 2026-04-01 |  | Open
SL-34 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley | Removal of loops/obstructions from a public footpath (access/safety improvement) | Sept 2025 | Sept 2025 | Closed | Green
SL-35 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley (bus shelter) | Arranged temporary safety mitigation (barriers/cones) following damage to Parish Council bus shelter | May 2025 | May 2025 | Closed | Green
SL-36 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley / Bridgnorth | Assisted two households with bulky waste removal (transport to tip) | May 2025 | May 2025 | Closed | Green
SL-37 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley | Supported a resident with housing-related queries and signposting | May 2025 | May 2025 | Closed | Green
SL-38 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley | Provided a laptop to a resident in the village (digital access support) | May 2025 | May 2025 | Closed | Green
SL-40 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Highley | Rhea Hall - unoccupied property. Neighbour complaint regarding vermin and infestation due to unhygenic state. | Feb 2026 | Feb 2026 | Open | Amber | EH visited property 12.03.26 and are liasing with neighbour
SL-44 | MC-15 | Direct Resident Support (Individual Cases) | Direct Support | Borle Brook Court, Highley | Ongoing support to resident including guidance on process and drafting formal correspondence to progress resolution. 17.03.26 Further guidance and drafted letter provided to the resident for the next stage. | Jan 2026 | 2026-03-01 | Closed | Green | Case raised in earlier monthly reports (historic issue not previously logged in tracker). Continued support provided 17/03/2026 including drafting follow-up letter. Resident engagement ongoing
SL-47 | MC-15 | First Point - maintenance services for Hitchen's Way | Direct Support | Highley, Hitchens Way | Concerns from 3 residents that the maintenance charges are high with double charging | 2026-02-01 |  | Open |  | Researched this issue, determined we need 50% of the residents to form an RTA to then challenge and replace First Port. Email sent 24.04 suggesting actions
SL-43 | MC-16 | Removal of Dilapidated Building | Planning Enforcement | Billingsley | Cape of Good Hope beyond repair, residents concerned and would like removed | Mar 2026 | Feb 2026 | Open
SL-48 | MC-17 | Request for Police Investigation into Offensive Political Messages Displayed on Vehicle in Bridgnorth Town Centre | Policing | Bridgnorth | Concerns from several residents and also parish councillors regarding messages deemed devisive. | 2026-03-01 |  | Open |  | Email sent to Officer Ives 4.04. requesting investigation
SL-50
SL-51
SL-52
SL-53
SL-54
SL-55

## Governance & Scrutiny
SL Ref | Master Case ID | Master Case Title | Category | Location | Issue / Activity | First Opened | Latest Update | Status
SL-24 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | Non-statutory services withdrawal pressure & spending priority debate | Feb 2026 | Feb 2026 | Closed
SL-25 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | Fees & Charges policy; £105m income target | Feb 2026 | Feb 2026 | Closed
SL-26 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | Deferred Payment Agreement fee increases | Feb 2026 | Feb 2026 | Closed
SL-27 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | 4.8% Social Housing rent increase | Feb 2026 | Feb 2026 | Closed
SL-28 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | 8.99% Council Tax increase approved | Feb 2026 | Feb 2026 | Closed
SL-29 | MC-12 | Governance & Financial Scrutiny | Governance | Council-wide | Five-year deficit forecast & EFS borrowing challenge raised | Feb 2026 | Feb 2026 | Monitoring